## Sheet1
Work Breakdown Structure Table
Provide basic information about the project including: Project Title – The proper name used to identify this project; Project Working Title - The working name or acronym that will be used for the project; Proponent Secretary - The Secretary to whom the proponent agency is assigned or the Secretary that is sponsoring an enterprise project; Proponent Agency – The agency that will be responsible for the management of the project; Prepared by – The person(s) preparing this document; Date/Control Number – The date the plan is finalized and the change or configuration item control number assigned.
Project Title: | Convention |  | Project Working Title:
Proponent Secretary: |  |  | Proponent Agency:
Prepared by: | Shondella Barkley |  | Date / Control Number: | 2016-04-25
Element Number | WBS Elements Activity, Task, or Sub-Task Name | Definition of Activity or Task (Description) | Responsible Person or Group | Estimated (E) or Actual (A) Cost (Cross reference to budget) | Project Phase (Cross reference to schedule)
1 | Location | Where will the convention be held Jackson Center | Shondella | 3700 | 1
2 | Hotel | Multiple hotels will need to be contacted in case one hotel cannot accommodate all the expected guests | Shondella | Comfort Suites $80.00 | 2
| Hotel | Pricing for Rooms | Shondella | Holiday Inn $95.00
| Hotel | Pricing for Rooms | Shondella | Westin $129.00
3 | Catering | Multiple food service providers will need to be contacted to ensure there is a backup service available in case the primary caterer encounters problems | Shondella | 425 | 3
| Catering |  | Shondella | 500
| Catering |  | Shondella | 685
| Catering |  | Shondella | 700
4 | Speaker | Contact 9 speakers for event three for each day and backups just in case someone can't make it. | Shondella | 300 | 4
| Speaker |  | Shondella | 200
| Speaker |  | Shondella | 300
| Speaker |  | Shondella | 1500
| Speaker |  | Shondella | 500
| Speaker |  | Shondella | 1000
| Speaker |  | Shondella | 200
| Speaker |  | Shondella | 400
| Speaker |  | Shondella | 700
| Speaker |  | Shondella | 300
| Speaker |  | Shondella | 500
| Speaker |  | Shondella | 500
5 | Travel | Contact airlines for travel for out of town guest | Shondella |  | 5
| Travel |  | Shondella
| Travel |  | Shondella
| Travel |  | Shondella
6 | Shuttle | Travel to and from airport for out of town guest | Shondella | 60 | 6
| Shuttle |  | Shondella